## Sheet1
Acquisition Transaction & Closing Checklist:
Activity | Timing | Level of | Who is |  | Follow-Up
for Closing Transaction | Complete | Priority | Accountable | Status | Action Required
Direct Marketing Letters to Potential Affiliate Sales Candidates/Prospects
Attorney and Accounting functions selected for your efforts
Strategy for "What to DO in the Event You BUY it?
Understanding of your company Marketing Plan to "New" Customers
LOI & Confidentiality Agreement Signed w/Term Outlined - Legal Approved
Draft agreement of a Non-Compete-Non Solicitation Key Employees
Development of Due Diligence - notes made (reference Questions)
Creation of a Business Plan - with Financial Model/Priorities Outlined
1. Letter from old owner and new owner to customers
2. Transition Stickers for Equipment - Marketing Ties to New Co.
3. Potential Open House for Existing Customers
Finalize Negotiations on Transaction Structure (asset Buy) - legal approved
Disposition of Employees - Agreements/Family
Disposition of Receivables - Collectable Portions
Disposition of Inventory - Count and Adjustment Reserve from Valuation
Disposition of any Work in Progress
Disposition of any Extended Warranties - Legal Reserves/Escrows
New Company/Acquiring Company Established
Signed Non-Compete & non-solicitation agreement
Final Physical Count of Inventory Performed - adjustment made to price
Receivables Report Defined - agreement on cash/receivables
Inventory and Receivables Adjustments made to Sale Price
Signed purchase agreement between parties - Receivables/WIP/ Reserves
Escrows/any sub agreements - employees - assets/inventory adjustments
If Partners - Must sign a Buy-Sell - Capital Agreement w/Insurance
Escrow Established - bank - for completion of transaction
Money Transfers to Complete Transaction
Select Key Employee Insurance Policy per Buy-Sell
Have a Company Employee Meeting - New Company/Plan
Meet Individually w/Employees of the company - 1 on 1/plan/role
Old Credit Cards Closed-Out
New Gas/Credit Cards Issued/transferred
Old co. Checking Account Closed
New Checking Accounts Opened if Necessary
Order A/P Checks New DBA Name
New Insurance Coverage - Liability
Certificates of Insurance
Truck Packages
License Plates Transferred to New DBA
Notify Municipalities and Inspectors
File for New Tax ID # New Co. DBA
New State #
Federal ID #
Notify BWC
Notify Unemployment
Update Withholding Tax ID's
W2's Created - Updated New Co.
Assign Depts in ADP
Create Workers Comp Report
New Paperwork-Spin To New ID
New Company Set-Up in Software
Vendor Credit Apps
File With State - HVAC/Plumbing License
PC Backups
Employee Manual Updated - released
Implement Employee Handbook
Execution of the Marketing Plan Above
Letter to All Vendors/Payables
Letter to All Employees Families
Letter to All Customers in Database w/Transition
Newsletter Marketing Offer to Customer Base (30 Day in)
Note on C22: Gary Elekes: Many companies have warranties they have sold and collected for but not reserved for and show the liability. As a matter of course, it is wise to 1. Ask about these types of warranties 2. Place a escrow for 1 year the amount equal to about 1-2% of purchase - goes to seller if no exceptions are found. This tends to raise the issues ASAP. It also insures the buyer - minimally.